ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background and other donor activities	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Consultant	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project intervention	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.1.1.	Project description	3

4.1.2.	Geographical area to be covered	3

4.1.3.	Target groups	4

4.2.	Specific activities	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Commencement date & Period of implementation	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Consultant	6

6.4.	Equipment	6

6.5.	Incidental expenditure	6

6.6.	Expenditure verification	6

7.	REPORTS	6

7.1.	Reporting requirements	6

7.2.	Submission & approval of reports	7

8.	MONITORING AND EVALUATION	7

8.1.	Definition of indicators	7

8.2.	Special requirements	7

# BACKGROUND INFORMATION

## Beneficiary country

Lebanon

## Contracting Authority

The Presidency of the Council of Ministers (PCM), represented by the Imprest Administrator and the Imprest Accounting Officer.

## Relevant country background and other donor activities

In 2005, following the Support to the Implementation of Association Agreement Project, the European Commission decided to provide a new flexible tool to support the definition and launch of a certain number of priority reforms. The first "Support to reforms" Programme (10 million EUR) was designed to provide a financially limited yet practically useful complement to the financial assistance that other donors may concede to the Government of Lebanon. Support to reforms II, III, Education & Public Finance Management Reform (PFM), Private Sector Reinforcement and Support to Reform and Environmental Governance projects largely follow the intervention logic of their predecessor.

The implementation of the ENP Action Plan and the work of the sub-committees set up under the Association Agreement, in consultation with stakeholders (civil society, private sector) provide an important framework in which priorities are detailed.

The sectors targeted by the related Financing Agreements (FAs) are, broadly speaking, government and private institutional infrastructure supporting the functioning of government.  The 3 Financing Agreements being implemented by the Presidency of the Council of Ministers (PCM) are: Education & Public Finance Management Reform (PFM), Private Sector Reinforcement (PSD) and Support to Reform and Environmental Governance (Streg).

The PAO was established at the Presidency of the Council of Ministers (PCM) in order to support the latter in the implementation of projects financed by the European Commission for which the PCM is the Contracting Authority.

## Current state of affairs in the relevant sector

The above-mentioned programmes managed by the PAO are instrumental in addressing strategic issues of improved governance in various sectors.  Specifically, the main domains covered by relevant programmes are: customs enhancement, taxation and quality-related legal and technical infrastructure, innovation, support to SMEs and to the business environment, public finance management, environment, and education. All of these are line with the ENP Action commitments, Paris III Commitment Documents, and Government Reform agenda.

The PAO is managed by a Project Director appointed by the PCM.  A Program Manager supervises the daily work and operations of the PAO, and reports to the Project Director.  All experts staff of the PAO report to the Program Manager.

## Related programmes

The FAs are complementary with other EU activities at both Regional (EuroMed Market programme, EuroMed Trade negotiations, etc) and bilateral levels. They also consolidate a series of EU-funded support to reforms actions under Support to Reforms - STR I and Support to Political and Socio-economic reforms (STR2), the trade-related activities will build upon the achievements and structures reinforced by the 2003 €16 million "Integrated Support to Small and Medium Enterprise", the €14 million ''Strengthening Quality Management, Capabilities and Infrastructures", which tackled trade, investment and production aspects at micro-economic level.

These projects complement on-going and planned EU funded projects, including in particular the Reconstruction facility, the “Quality”, the “SME”, the "Economic and Social Fund", the "Agriculture" and "Security" programmes, as well as the “Support to Civil Society (AFKAR 2)” and local governance programmes.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To support the Government of Lebanon in the implementation of its reform priorities defined by the government in its Reform Programme (Paris III, January 2007), in the joint EU-Lebanon ENP Action Plan and the Ministerial Declaration of the New National Unity Government of December 2009.

## Purpose

The purpose of this contract is as follows:

To support the PAO (which in turns supports the Contracting Authority PCM) with expertise in implementing EU-funded programmes.

## Results to be achieved by the Consultant

For its responsibility areas, the EU-funded programmes are managed in a timely and efficient manner, in line with the EU rules and dispositions and in accordance with the technical and administrative provisions of the STReg Financing Agreement.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

- Political environment is stable

- Stakeholders are willing and available to cooperate

- Required legislations for the implementation of activities are enacted

- Continued commitment to reform agenda by government

- Staff required for the implementation is available/recruited and for sustainability is retained

## Risks

- Unstable security situation might affect the project implementation

- Discontinuity of involvement of stakeholders

# SCOPE OF THE WORK

## General

## Project description

The Program Manager at the PAO is responsible for the appropriate implementation of EU-funded programs for which the PCM is the Contracting Authority and ensure that deliverables are submitted in an effective and timely manner.  The Program Manager manages the daily operations of the PAO.

The Program Manager reports to the Project Director.

## Geographical area to be covered

Lebanon

## Target groups

Various government agencies, ministries, and private entities with public benefits including and not limited to: Ministry of Finance, Ministry of Industry, Ministry of Education and Higher Education, Ministry of Economy and Trade, Ministry of Environment, Industrial Research Institute, Kafalat, Business Development Centres, and incubators.

## Specific activities

On an indicative basis:

- Support the Project Director in the overall management of the financing agreements, especially in ensuring the smooth and efficient daily operations of the PAO.

- Prepare a master project plan (workplan) for the entire EU funded programmes for which the PCM is the Contracting Authority and update it periodically. The project plan contains all deliverables and milestones of all projects and activities under the financing agreements being implemented. - Prepare the master projects implementation milestones for all PAO projects, and inform the EU Delegation on timely implementation. - Ensure the timely execution of projects for which the PCM is the Contracting Authority.

- Follow up on project related decisions taken by the Council of Ministers.

- Attend projects’ steering committee meetings if needed and follow up on results and recommendations.

- Follow up on recommendations of auditors and monitors.

- Ensure proper maintenance of program-related documentation and archive. - Distribute workload among PAO staff and coordinate smooth cooperation between team members. - Assist the Project Director in ensuring good collaboration between beneficiaries, the PCM, and the EU Delegation. - Compile reports on performance of PAO, and draft correspondence and/or documentation related to the implementation of EU-funded projects for which the PCM is the Contracting Authority. - Act as a National Contact Point for TAIEX; review requests and ensure that they are in line with EU rules and EU Lebanon Action Plan and that they complement other initiatives, suggest participants for regional TAIEX workshop, raise awareness and ensure full use of the TAIEX, and report on instrument use. - Act as National Contact Point for SIGMA; review SIGMA requests, monitor implementation, raise awareness on SIGMA, and report on instrument use. - Act as National Contact Point for Twinning; fulfil the responsibilities required from PAO in regards to Twinning as per the Twinning Manual. Ensure proper coordination with Twinning Beneficiaries, especially when PAO is not the Contracting Authority. Raise awareness on twinning and report on instrument use. - Other tasks as deemed necessary by the Project Director

## Project management

### Responsible body

The Contracting Authority shall be the Presidency of the Council of the Ministers (PCM), represented by the Imprest Administrator and the Imprest Accounting Officer.

### Management structure

The Project Director of the PAO will be responsible for the approval of all deliverables and will therefore fulfil the tasks of the Project Manager for this contract.

### Facilities to be provided by the Contracting Authority and/or other parties

Office accommodation of a reasonable standard and of approximately 10 square metres for the expert working on the contract is to be provided by the Presidency of the Council of Ministers. The PCM shall ensure that expert is adequately supported and equipped.

# LOGISTICS AND TIMING

## Location

The location will be the premises of the Project Administration Office (PAO) at the Presidency of the Council of Ministers (PCM).  On-site visits to beneficiary institutions in Beirut and to projects in Lebanon will also be necessary.

## Commencement date & Period of implementation

The intended commencement date is January 2015 and the period of implementation of the contract will be 18 months from this date. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

The expected effort needed is a maximum of 360 man/days to be executed before end of June 2016.  The Consultant cannot invoice during vacation and official public holidays.

# REQUIREMENTS

## Personnel

### Key experts

Note that civil servants and other staff of the public administration, of the partner country or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

Key expert 1: Program Manager

Qualifications and Skills:

- Graduate degree in public administration, economics, development, or other relevant fields.

- Fluency in speaking, writing, and reading Arabic and English. French would be an asset.

- Advanced proficiency in the use of computers and Microsoft office (Word, Excel, Power point) and project management software.

General Professional Experience

- Minimum of 15 years of total work experience.

- Minimum of 10 years of project management experience; PMP certification is an asset.

Specific Professional Experience

- Minimum of 1 year of experience in the Lebanese public sector or in the public administration of European Neighbourhood Policy Partner Countries in Southern Mediterranean (Southern ENP).

- Experience in EU rules and procedures or of the ones of similar international donor agencies is considered an asset.

The expert must be independent and free from conflicts of interest in the responsibilities he takes on.

### Other experts

Not applicable.

## Office accommodation

Office accommodation of a reasonable standard and of approximately 10 square metres (including appropriate standard office tools as well as office automation tools) for the expert working on the contract shall be provided by the Presidency of the Council of Ministers.

## Facilities to be provided by the Consultant

Not applicable.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / beneficiary country as part of this service contract or transferred to the Contracting Authority / beneficiary country at the end of this contract. Any equipment related to this contract which is to be acquired by the beneficiary country must be purchased by means of a separate supply tender procedure.

## Incidental expenditure

Not applicable.

## Expenditure verification

The Provision for expenditure verification relates to the fees of the auditor who has been charged with the expenditure verification of this contract in order to proceed with the payment of further pre-financing instalments if any and/or interim payments if any.

The Provision for expenditure verification for this contract is EUR 1,500. This amount must be included without modification in the Budget breakdown. This provision cannot be decreased but can be increased during execution of the contract.

# REPORTS

## Reporting requirements

A progress report must be prepared every six month. It must be provided along with the corresponding invoice, the financial report and an expenditure verification report defined in Article 28 of the General Conditions. The report shall include a short description of achievements including problems encountered and recommendations.

There must be a final report, a final invoice and the financial report accompanied by an expenditure verification report at the end of the period of implementation of the tasks. The draft final report must be submitted at least one month before the end of the period of implementation of the tasks. Note that these interim and final reports are additional to any required in Section 4.2 of these Terms of Reference.

Each report shall consist of a narrative section and a financial section. The narrative section must include major accomplishments and results, challenges, and lessons learned / recommendations.  The financial section must contain details of the time inputs of the experts and of the fees for expenditure verification.

To summarise, the consultant shall provide the following reports:

| Name of report | Content | Time of submission |
| --- | --- | --- |
| Inception Report | Analysis of existing situation and plan of work for the project | No later than 1 month after the start of the implementation |
| 6 monthly Progress Report | Short description of progress (technical and financial) including problems encountered; planned activities for the ensuing 6 months accompanied by an invoice and the expenditure verification report. | No later than 1 month after the end of each 6 month implementation period |
| Draft Final Report | Short description of achievements including problems encountered and recommendations | No later than 1 month before the end of the implementation period. |
| Final Report | Short description of achievements including problems encountered and recommendations; a final invoice and the financial report accompanied by the expenditure verification report. | Within 1 month of receiving comments on the draft final report from the Project Manager identified in the contract. |

## Submission & approval of reports

In view of environmental considerations, electronic documents should be used instead of paper copies whenever possible.  The reports referred to above must be submitted to the Project Manager who is the PAO Project Director (see 4.3 above). The reports must be written in English. The PAO Project Director is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Not applicable.

## Special requirements

Not applicable.

* * *